## Read me
Federated adoption tracker
For change in an organization where nobody has to say yes: autonomous units, balanced governance, hard local constraints, voluntary adoption.
The five sheets
Units - one row per unit, with capacity, autonomy and who actually decides there.
Constraints - the register the whole design rests on. Type, source, effect, response, review date.
Ladder - where each unit sits on the five rungs, and the single next step for each. This is your weekly working sheet.
Decisions - the consent log: proposal, objections raised, how each was integrated, and the three clauses.
Dashboard - ladder distribution, referrals, constraint resolution. Computed, never typed.
Two rules
Track the rung and the next step per unit, not a programme plan. A federation where nobody moved a rung in a quarter has a stalled change, whatever the activity looks like.
Record constraints in their words with the source named - or 'not yet identified'. Never write the word preference where anyone can read it.
The metric that predicts everything else is unit-to-unit referrals: conversations between units with central not in the room.
Companion article: mehdibamou.com/publications/governing-without-a-mandate - free to use and adapt

## Units
Unit ID | Unit | Size band | IT capacity | Who decides here | Working language | Last visited | Visit type | Champion | Notes
U-01 | Unit North | Large | Team of ~30 | Director, with board sign-off over a threshold | EN | 2026-03-11 | In person | Yes - ops lead | Reference implementation risk: designs skew to their scale
U-02 | Unit East | Small | 0.25 FTE | Director alone | EN, local | 2026-04-22 | In person | Yes - director | Capacity is the binding constraint, not willingness
U-03 | Unit South | Medium | 2 people | Management team, monthly | FR | 2025-11-06 | Remote | Not yet | Sceptical after a previous central rollout
U-04 | Unit West | Medium | 1 person | Director plus member assembly | ES |  | Not yet | Unknown | In the rotation for the coming year
^ start here. One row per unit. 'Who decides here' is the field people skip and then wonder why proposals stall.

## Constraints
ID | Unit | Type | Stated constraint (their words) | Source | Effect on design | Possible response | Status | Review date
C-01 | U-02 | Funding | We cannot spend on this in this budget cycle | Restricted grant funding, confirmed by their finance lead | Cannot pay a per-unit fee before next cycle | Central hosting for year one, staged fee from year two | Open | 2026-10-01
C-02 | U-03 | Legal | Records may not leave the country | National rule, citation to confirm | Rules out a single shared instance abroad | Regional deployment option, or local cache with shared definitions | Open | 2026-09-15
C-03 | U-01 | Technical | Partner contract requires their platform until 2029 | Contract, signed 2023 | Interface must accept their export format | Adapter to the canonical profile | Open | 2029-01-01
C-04 | U-04 | Political | Director cannot commit without the assembly | Statutes | Timing: proposals must land before the assembly cycle | Two-pager they can forward, timed to their calendar | Open | 2026-11-30
C-05 | U-03 | Capacity | No one to administer another system | Stated, source not yet identified | Ceiling on local complexity for the whole design | Zero-admin profile; revisit after their hire | Softened | 2026-12-01
^ start here. Type drives the response - see the article. Status: Open, Softened, Resolved, or Superseded.

## Ladder
Unit ID | Unit | Rung | Rung no | Since | The single next step | Owner of next step | Referrals made | Blocked by (constraint ID)
U-01 | Unit North | Adopting | 4 | 2026-02-10 | Present their cost figures at the spring forum | Their ops lead | 2
U-02 | Unit East | Piloting | 3 | 2026-05-04 | Minimum profile file for one month, hosted centrally | Me | 0 | C-01
U-03 | Unit South | Interested | 2 | 2026-06-18 | Send the two-pager in French, then call in three weeks | Me | 0 | C-05
U-04 | Unit West | Aware | 1 | 2026-07-02 | Visit in the rotation; time the proposal to their assembly | Me | 0 | C-04
^ start here. Rung: Aware(1) Interested(2) Piloting(3) Adopting(4) Advocating(5). One next step per unit - if you cannot name it, that is the finding.

## Decisions
Ref | Date | Proposal | Body | Outcome | Objections raised | How integrated | Sunset | Review trigger | Opt-out / profile
P-01 | 2026-03-24 | Adopt the minimum exchange profile as the shared way | Assembly | Consented | Two: cost for small units; timing against one budget cycle | Central hosting added for units under a size threshold; start date moved by one quarter | 2027-09-30 | If more than two units report the profile unworkable | Units may send the monthly file instead of the interface
P-02 | 2026-06-09 | Shared identity for cross-unit staff | Assembly | Deferred | One: data residency unresolved for two units | Parked with named owner; regional option to be designed and brought back |  | When the residency option is designed | Not yet drafted - this is why it was deferred
^ start here. Record objections even when integrated - the trend in objection themes is one of your best metrics.

## Dashboard
Adoption at a glance
Computed from the other sheets. Nothing here is typed.
Ladder distribution
Rung | Units | Share | Interpretation
Aware | 1 | 25% | Know it exists
Interested | 1 | 25% | Asked a real question
Piloting | 1 | 25% | Something is running
Adopting | 1 | 25% | Their normal way
Advocating | 0 | 0% | Explaining it to peers without you
Units tracked | 4
The numbers that matter
Past piloting (rung 3+) | 2 |  | The inversion happens around a third of units
Share past piloting | 50% |  | Watch this, not compliance
Unit-to-unit referrals | 2 |  | Predicts everything else - the day it beats your outreach, it is self-sustaining
Units visited in person | 2 |  | Six to eight in year one is realistic
Open constraints | 4 |  | The register earning its keep
Constraints softened or resolved | 1 |  | Half of soft constraints dissolve within a year
Proposals consented | 1 |  | Permission, not adoption
Proposals deferred | 1 |  | Deferral is the default failure mode - integrate objections earlier
Never track compliance rate. It is near zero for a year and then jumps, and neither number tells you whether you are winning.