## Slide 1
THE DATA MODEL IN A CLEAN CORE PROGRAMME
Six moves, one worked object,
and a cutover that closes
How the object model turns clean core from a slogan into a lookup: mastership published before the design workshops, the attribute triage, localization as a data question, and a dual-write window with an expiry date
Companion to mehdibamou.com/publications/data-strategy-object-model

## Slide 2
WHY THIS DECK EXISTS
Most "we need a modification" requests are ownership disputes
What arrives at the design session, and what is actually being negotiated
mehdibamou.com - free to use and adapt
What the request says | What it usually is | What answers it
"The standard cannot handle our supplier verification" | Their local register masters supplier data and nobody told them it will not | The mastership list, published before the workshop
"We need one more field on the customer screen" | Nobody has decided whether that field is a group attribute or a local one | The attribute triage - three answers, decided by looking
"This is a legal requirement in our market" | Sometimes true. Often a preference that has been true for a decade | The jurisdiction-scoped attribute list, which is short and checkable
"Our data cannot leave the country" | Almost always true, and nobody can say where it sits today | The object-to-IT-component join
"We will keep our system running alongside" | Reasonable, and unregistered - which is the actual problem | A reference copy with a purpose and an expiry date
Answer the ownership question first and the functional conversation gets shorter, calmer, and more honest. Expect the argument - it is finite, once per object, and then it is written down.

## Slide 3
THE SEQUENCE
Six moves, in this order
Each one is cheap. The order is what makes them work
mehdibamou.com - free to use and adapt
1
Mastership before modules
Publish the object mastership list before the functional design sessions. One afternoon of publishing, two uncomfortable weeks of argument
2
The attribute triage
Group key attribute, jurisdiction-scoped, or local. Same request, three completely different answers, decided by lookup rather than by argument
3
Localization as a data question
Statutory attributes flagged and scoped on the factsheet. "Build it once" stops being an aspiration and becomes a row somebody points at
4
Interfaces follow the model
The canonical shape is the key attribute list. One owner per object is integration rule two. Two documents, one set of facts
5
Residency by the component join
A query, not an investigation. Sometimes bad news - but on day four rather than in the second week of user acceptance testing
6
The cutover
Mastership move with a dual-write window that is a registered exception with an expiry, not an understanding between two teams

## Slide 4
MOVE ONE
Publish mastership before the design workshops
The highest-yield thing in a programme of this kind, and it costs an afternoon
mehdibamou.com - free to use and adapt
WHAT YOU PUBLISH
Object | Master | Owner
Supplier | Core ERP | Procurement ops
Customer | CRM | Head of CRM
Material | Core ERP | Master data
Price | Core ERP, moving Q4 | Pricing
Employee | HR system | People ops
HOW TO PUBLISH IT
Send the list to every market lead and every workstream lead, in one message, with one sentence: this is the current proposal, tell us where it is wrong within two weeks.
Say out loud that a mastership decision made privately reads as arbitrary and gets relitigated forever. Making it in public, early, is what makes it stick.
The objections you get back are the real design input. Most of them are about two or three objects, and those are the ones worth a board decision.
WHAT IT PREVENTS
A market discovers in month five that their system no longer masters something. By then the functional design assumes it does, the interfaces have been built, and the conversation is not a design conversation any more - it is an escalation with a schedule attached.

## Slide 5
MOVE TWO
The attribute triage
"We need one more field" - the same request, three answers, decided by looking rather than arguing
mehdibamou.com - free to use and adapt
OUTCOME 1
Group key attribute
TEST
Every market needs it and it is not market-specific
WHERE IT GOES
In-app extension, registered. The factsheet gains an attribute, applied everywhere
RESULT
Upgrade-safe. One decision, one build
OUTCOME 2
Jurisdiction-scoped and statutory
TEST
Somebody can name the law, the regulator, or the reporting obligation
WHERE IT GOES
Localization layer, built once per requirement. Factsheet records the jurisdictions
RESULT
Upgrade-safe. The second market asking gets pointed at a row
OUTCOME 3
Local and not statutory
TEST
Real for this market, no legal basis, no group need
WHERE IT GOES
Side-by-side or the fit-gap list. Factsheet records it as local, with an owner and a review date
RESULT
The core stays clean and nobody was told their requirement was invalid
First, always: can configuration do it? Check the country versions and the modules nobody activated. A striking share of "impossible" requests are switched off rather than absent.

## Slide 6
MOVE THREE
Localization becomes a data question
The statutory bucket finally has somewhere to live
mehdibamou.com - free to use and adapt
BEFORE - AN ARGUMENT
A market says a field is legally required. Somebody disagrees. The discussion is about who is more credible, and it happens again in the next market, and again in the one after that.
Nobody can produce a list of what is genuinely statutory, so nobody can say how much of the programme is legal requirement and how much is habit.
AFTER - A FIELD
The factsheet has a jurisdiction-scoped attribute list. A statutory field goes on it, with the jurisdictions named. A preference does not.
The register that falls out is both the localization backlog and the honest answer to how much of this programme is legal requirement.
Object | Attribute | Jurisdictions | Built where | Status
Supplier | Tax identifier format | A, B, C, E, F | Localization layer | Live, one build
Supplier | Statutory address | B, E | Localization layer | Live, one build
Supplier | Payment reporting flag | E | Localization layer | Live, one build
Customer | Consent basis and record | All | Core, scoped | Live
Employee | Statutory contract fields | C, F | Localization layer | In build
In one programme the honest figure was under fifteen per cent of what had been claimed. Having the list made that a calm conversation rather than an accusation.

## Slide 7
MOVE FOUR
The interface layer follows the model
Not a coincidence - the integration standard and the data model are one document seen from two sides
mehdibamou.com - free to use and adapt
Integration rule | What the model supplies
Released contracts only | The object's contract list, with direction and pattern, from the object-to-interface join
One owner per data object | The master field on the factsheet. This rule IS the data model, restated
Canonical shape in the middle | The key attribute list. Dialects translate at the edge; the canonical form is the eight to fifteen attributes people argued about
Thin middleware | Business rules belong to whoever owns the object, side-by-side, not in transformation logic nobody owns
Async by default | The latency the factsheet promises consumers is what makes async acceptable to them
Idempotent and replayable | The identifier scheme and cross-reference table are what make a second arrival safe
Maintained separately, the two disagree within two quarters - and the disagreement is discovered by a delivery team at the worst possible moment. One owner, one list, two views.

## Slide 8
MOVE FIVE
Residency answered by the component join
The conversation that used to take six weeks
mehdibamou.com - free to use and adapt
THE QUESTION
"Our customer data cannot leave the country. Where does it sit today?"
WITHOUT THE MODEL
Four vendors, three architects and about six weeks. The answer arrives incomplete, and the incompleteness is discovered later by an auditor.
WITH THE MODEL
Filter Links for the object, type "object to IT component".
Each row names the component, the region, and the market it serves.
Cross-check the open exceptions for anything already registered.
Four days, including the part where you verify two of them by hand because you do not fully trust the record yet.
THE UNCOMFORTABLE PART
Sometimes the answer is bad news: data is somewhere it should not be, or the target design moves it somewhere the market cannot accept.
That is bad news on day four rather than in the second week of user acceptance testing, which is an entirely different kind of bad news - one that still has options attached to it.
The residency answer is the single clearest return on the object-to-IT-component join, and the reason the application versus component distinction is worth the pedantry.

## Slide 9
MOVE SIX
The mastership move runbook
The riskiest event in any migration, because for a period two systems are both writing and both believe they are right
mehdibamou.com - free to use and adapt
Step | Do | Recorded where
T minus 8 weeks | Board decision on the move, with the date and the dual-write window length | Decision log, and the factsheet
T minus 6 weeks | Register the dual-write window as an exception with an expiry date | Exception register
T minus 4 weeks | Publish the consumer list from the join table. Every consumer confirms which system they will read from, and when they switch | Links sheet, plus a line per consumer
T minus 2 weeks | Reconciliation rule agreed - which system wins on conflict, and who is called when it happens | Factsheet note, and the runbook
Cutover | New master goes live. Old master becomes a system of reference with a stated end date | Links: role changes from Master to Reference, expiry set
Window open | Daily reconciliation count published. A rising count is a rollback signal, not a nuisance | The programme report
Window closes | Old write path switched off. Exception closed. Factsheet change log updated | Exception register, factsheet
T plus 4 weeks | Confirm the old master has no writes. Only now is the move done | Attestation by the object owner
I have seen a dual-write window meant to last three weeks run for two years, entirely because nobody wrote down when it should end. An expiry date in a register costs thirty seconds.

## Slide 10
THE WORKED OBJECT
Supplier, before and after one quarter
Figures illustrative, shape exact
mehdibamou.com - free to use and adapt
BEFORE
Three masters and nobody sure
3
systems appearing as master, depending on who you asked
~40
custom fields accumulated in the core over a decade
4
definitions in circulation. The carrier argument had been had three times
2
local registers, unregistered and invisible to the programme
6 wks
to answer where a market's data physically sat
AFTER ONE QUARTER
One master, two references with dates
1
system of record, published before the design workshops
11+3
group key attributes, plus jurisdiction-scoped ones
1
definition, with a boundary line. The carrier argument has not recurred
2
local registers kept as side-by-side systems, with contracts and expiry dates
4 days
to answer the residency question
And six of the forty custom fields retired - not by campaign, but because nobody could name the decision they fed. Six is not a triumph. It is evidence that the question works.

## Slide 11
DURING THE PROGRAMME
Keeping the model true while everything is moving
A programme generates more object change in a year than the previous five combined
mehdibamou.com - free to use and adapt
Event | Who acts | What updates | Where it is checked
A workstream proposes a new field | Steward classifies against the triage | Attributes sheet | Design forum, weekly
A market requests an extension | Architect classifies against the four places | Extension register and, if relevant, the factsheet | Design forum, or board if mastership moves
An interface is built | Integration lead registers it | Links: object to interface | Gate two
A system is added to the landscape | Architect adds the object links with roles | Links: object to application | Gate two
Data is moved to a new component | Infrastructure lead updates the component link | Links: object to IT component | Quarterly attestation
Mastership moves | Board decides; owner executes the runbook | Factsheet, Links roles, exception register | Board, then attestation at T plus 4 weeks
A policy changes | Object owner edits one factsheet | Factsheet, then the model generates the scope list | Owners' circle, quarterly
Nothing in this table is a new meeting. Every row lands in a forum or a gate that already exists, which is the only reason the model is still accurate when the programme ends.

## Slide 12
REPORTING
Four lines in the report that already goes out
No new report. No new meeting. No new governance body
mehdibamou.com - free to use and adapt
LINE 1
9 of 10
Objects with a single confirmed master
The headline. One contradiction, named, with a board decision attached
LINE 2
0
Open reference copies past expiry
An unauthorized copy as of today, which is a different thing from an approved one
LINE 3
8 of 10
Objects attested this quarter
The leading indicator. An object unattested for a year has an owner who stopped reading
LINE 4
31
Extensions classified as local, not statutory
The localization honesty check. It should fall every quarter of a clean core programme
THE RULE FOR ALL FOUR
Report the specific items, not only the totals. "Nine of ten objects have a single master" is a statistic. "Price has two masters, board decision ADR-092, window closes 24 December" is a thing somebody does something about.

## Slide 13
STARTING
If the programme has already begun
Which is the normal case, and it changes only the order
mehdibamou.com - free to use and adapt
DO THIS WEEK
1
List the objects from the interfaces the programme has already designed - that list exists and nobody has read it as an object list
2
Name a master for the ten that appear most often. Publish it as a proposal with a two-week objection window
3
Take the top three disputes to the board with a decision paper each, rather than letting them run as workstream friction
4
Add the gate question to whatever intake form the programme already uses
5
Write factsheets for the ten, one page each, aliases and boundary lines included
DO NOT
x
Do not buy a catalog, an MDM platform or a quality tool. All of them get better once the decisions exist and none of them substitutes for making them
x
Do not model more than fifteen objects in the first pass. A hundred and forty objects is a monument, not a model
x
Do not create a data governance board. Three quarters of the decisions belong in the design forum you already run
x
Do not write a definition before somebody has pulled two hundred rows and read them
x
Do not run the model as a project. Accurate on day one, fiction by month nine - the wiring into the gates is the deliverable
The mastership argument is unpleasant, finite, and the whole point. Skip it and you have written down the current confusion in a neater font.