## Read me
Decision and register workbook
Four registers on one shared shape, plus the links that make records surface later and the derived views that tell you whether the practice is working.
The shape, in every register
Chose, Rejected, Why, Cost we accept - plus ID, date, decider, status, and links. If two registers use different shapes nobody can read across them, and reading across them is where the value compounds.
Why four registers rather than one
Because the clocks differ. Directions run until superseded, exceptions expire on a date, assessments refresh on a cycle, classifications hold until the underlying fact changes. A register whose entries expire on four clocks cannot be reviewed as one thing.
The sheets
Decisions - directions, selections and dispositions. The main log.
Exceptions - permitted violations, each with an expiry and a closure condition.
Classifications - values set on repository records, with the rationale that is normally lost.
Assessments - judgements at a point in time, with the rater, the anchor cited, and the next cycle.
Links - one flat table joining any record to the applications, objects, domains, interfaces and projects it touches.
Derived views - health of the practice: expiring records, missing fields, repetition, and the records nobody has ever cited.
How to run it
1. The decider writes the record, at the moment, in about twenty minutes. If it takes longer, the decision has not been made yet.
2. Route by clock: does it break a rule (Exceptions), set a value on a record (Classifications), express a judgement that refreshes (Assessments), or bind future designs and purchases (Decisions).
3. Add rows to Links for everything the record touches. Without links a record is findable only by somebody who already knows it exists.
4. Read Derived views monthly. The repetition counter is the one that pays - the same topic arriving three times is a missing principle announcing itself.
5. Never delete. Set status to superseded and point forward in the Supersedes / superseded-by columns.
Two fields people leave out, and should not
Rejected - without it nobody can tell whether their idea was examined and dismissed, or never occurred to anybody. Both are common and need different conversations.
Cost we accept - a decision with no stated cost was a preference.
Yellow cells are yours to fill. Everything else computes.
Companion article: mehdibamou.com/publications/decision-records - free to use and adapt

## Settings
Setting | Value | Note
As-at date | 2026-08-20 | Drives expiry countdowns and staleness
Warn before expiry (days) | 60 | How early a record shows as due
Assessment cycle (months) | 6 | After this an assessment is stale
Repetition threshold | 3 | Same topic this many times means a missing principle

## Lists (hidden)
Direction | Proposed | Open | Application | Business fit
Selection | Accepted | Closed | IT component | Technical fit
Disposition | Superseded | Extended | Object | Capability maturity
| Rejected | Expired | Domain | Data quality
Interface
Project
Capability

## Decisions
ID | Kind | Date | Decided by | Topic | Chose | Rejected | Why | Cost we accept | Status | Supersedes | Superseded by | Review date | Days to review
ADR-018 | Direction | 2023-10-04 | Design forum | Price mastership | Price is mastered by the commerce platform | Mastering price in the core, which nobody wanted to configure at the time | Commerce was the only system with a pricing screen and the core rollout had not started | The core consumes price from commerce, which reverses the usual direction | Superseded |  | ADR-041
ADR-041 | Direction | 2024-11-12 | Architecture board | Price mastership | Price is mastered by the core | A separate pricing engine, judged premature with one market live | Only one market was live and the condition technique covered the rules then | Pricing rules stay within what the standard can express | Superseded | ADR-018 | ADR-092
ADR-063 | Direction | 2025-07-03 | Architecture board | Core integration | Every interface to the core uses a released API or event | Direct table reads, which two existing interfaces already used | Two direct reads built in 2022 broke the last upgrade and cost a weekend | Some interfaces wait for the vendor to publish an API | Accepted
ADR-071 | Direction | 2026-01-13 | Architecture board | Customer copies | Campaign tool reads customer via API and holds no authoritative copy | A local customer store, which would have shipped the campaign three weeks earlier | Three of last year's four data incidents came from two systems owning one object | The campaign shipped two weeks later than hoped | Accepted
ADR-088 | Direction | 2026-01-27 | Design forum | Event broker | Defer the broker choice until a second producer exists | Choosing now on one producer and a proof of concept | A single producer does not exercise load, replay or operability | First producer ships on the existing queue and will migrate, roughly two weeks of rework | Accepted |  |  | 2026-09-30
ADR-092 | Direction | 2026-06-09 | Architecture board | Price mastership | Price becomes mastered by the side-by-side pricing service from the Q4 cutover | Extending the condition technique in the core. Mastering price in commerce, dismissed because commerce consumes every other object | The rules the business needs cannot be expressed without a core modification, and we are counting those down | Eight weeks of dual write and a reconciliation nobody wants to run | Accepted | ADR-041
SEL-07 | Selection | 2026-03-18 | Steering committee | Warehouse system, market D | Vendor B | Vendor A, excluded on mandatory M-1 (cannot operate against externally mastered data, demonstrated live). Vendor C withdrew at shortlist | B met all three mandatory criteria; the commercial gap was decisive and the architecture gap judged recoverable through configuration | B publishes events by polling. We accept latency on stock updates, written into the contract | Accepted |  |  | 2029-04-02
DSP-22 | Disposition | 2026-05-06 | Domain architect | Market F picking sequence | Fit-gap list with a twelve-month review | Building it side-by-side, or a core modification | No legal basis and no group need. The warehouse layout predates the standard | Market F retrains staff on the standard sequence | Accepted |  |  | 2027-05-06

## Exceptions
ID | Raised | Deviates from | Why | Approved by | Owner | Expiry | Days to expiry | Renewals | New reason on last renewal? | Closure condition | Status | Closed
EXC-09 | 2024-09-30 | No local supplier stores outside the core and the two registered registers | Six-month workaround pending the onboarding service | Architecture board | Procurement IT | 2026-03-31 |  | 2 | No | Onboarding service live in this market | Closed | 2026-07-12
EXC-10 | 2026-03-03 | Contract data held only in the core | Residency requirement, statutory | Compliance lead | Legal IT |  |  | 0 | - | Permanent - statutory | Open
EXC-11 | 2026-06-09 | One system of record per object (P-01) | Cutover requires dual write for eight weeks | Architecture board | Named architect | 2026-12-24 |  | 0 | - | Old write path off, confirmed by the object owner | Open
EXC-12 | 2025-08-05 | Promotion mastered in the core | Tool predates the programme; migration in wave three | Architecture board | Marketing IT | 2026-04-30 |  | 1 | Yes | Wave three complete | Open
EXC-13 | 2026-02-17 | Every interface uses a released contract (ADR-063) | Vendor has not published the API; bridge in place | Design forum | Integration team | 2026-09-30 |  | 0 | - | Vendor API published and consumed | Open
An extension without a new reason is a rejection with better manners. Column J is the tell that the quarterly review has stopped happening.

## Classifications
ID | Date | Record | Record type | Field set | Chose | Rejected | Why | Cost we accept | Decided by | Review trigger
CLS-014 | 2026-02-11 | APP-077 | Application | Application or IT component | One application | Three IT components under a notional parent | Business users interact with it directly, which is the line we apply everywhere. The parts have no independent lifecycle and no separate owner | Per-part end-of-support reporting moves to a note on the record | Portfolio owner | When the semantic layer is replaced
CLS-015 | 2026-03-04 | OBJ-04 | Object | Definition boundary | A supplier is a legal entity we can raise a purchase order against | Including carriers and one-off payees, as finance wanted | Carriers have a different lifecycle and different statutory handling | Finance keeps a separate payee list and reconciles monthly | Data steward | If the payment process changes
CLS-016 | 2026-04-22 | APP-118 | Application | Lifecycle and sunset | Phase-out with sunset 2027-06-30 | Retain, which the market argued for | The onboarding service covers the capability from wave two, and the licence renews in 2027 | The market runs both for one quarter during transition | Application owner | At wave two go-live
CLS-017 | 2026-05-19 | OBJ-01 | Object | Residency classification | Customer data for markets B, E and G stays in-country | One EU region for all markets, which is cheaper | Three markets have statutory residency requirements naming the jurisdiction | Three additional database instances and their operating cost | Compliance lead | On any new market
The register almost nobody keeps. These are the calls that change counts, ownership and budgets for years, and they are normally recorded nowhere.

## Assessments
ID | Date | Record | Scale | Chose | Rejected | Anchor cited | Why | Rated by | Disputed? | Next cycle | Days since
ASM-2026-Q2-APP-118 | 2026-05-04 | APP-118 | Business fit | 2 | 3 | "Does the job with accepted workarounds" is the anchor for 3 | Two of four core steps are done outside the system in a spreadsheet maintained by one person. A core gap filled by a shadow tool is the published anchor for 2 | Head of procurement ops | Yes | 2026-11-04
ASM-2026-Q2-APP-118T | 2026-05-04 | APP-118 | Technical fit | 2 |  | "Components approaching end of support" is the anchor for 2 | The database version is out of support in eleven months and the integration is a file drop with no schema | Integration team | No | 2026-11-04
ASM-2026-Q2-APP-002 | 2026-05-11 | APP-002 | Business fit | 3 |  | "Does the job with accepted workarounds" | Two markets maintain parallel spreadsheets for reporting, accepted and understood | Head of order management | No | 2026-11-11
ASM-2025-Q4-APP-070 | 2025-11-18 | APP-070 | Technical fit | 2 | 3 | "Integration debt accumulating" | Three point-to-point interfaces with no contracts, all built in one quarter | Integration team | No | 2026-05-18

## Links
Link ID | Record ID | Register | Linked type | Linked ID | Linked name | Note
L-001 | ADR-092 | Decisions | Object | OBJ-07 | Price
L-002 | ADR-092 | Decisions | Application | APP-002 | Core ERP | loses mastership
L-003 | ADR-092 | Decisions | Application | APP-131 | Pricing service | gains mastership
L-004 | ADR-092 | Decisions | Domain | DOM-05 | Pricing and promotion
L-005 | EXC-11 | Exceptions | Object | OBJ-07 | Price | dual write window
L-006 | ADR-063 | Decisions | Interface | INT-010 | Old finance interface | the one this decision forbids
L-007 | ADR-063 | Decisions | Domain | DOM-10 | Corporate platforms
L-008 | ADR-071 | Decisions | Object | OBJ-01 | Customer
L-009 | ADR-071 | Decisions | Application | APP-090 | Campaign tool
L-010 | CLS-014 | Classifications | Application | APP-077 | Data platform
L-011 | CLS-017 | Classifications | Object | OBJ-01 | Customer | residency
L-012 | CLS-017 | Classifications | IT component | ITC-052 | Market G database, in-country
L-013 | SEL-07 | Decisions | Project | PRJ-0426 | Replace the market D warehouse system
L-014 | SEL-07 | Decisions | Application | APP-119 | Market D warehouse system
L-015 | EXC-09 | Exceptions | Project | PRJ-0418 | Supplier onboarding for market D | the project that closed it
L-016 | EXC-09 | Exceptions | Object | OBJ-04 | Supplier
L-017 | ASM-2026-Q2-APP-118 | Assessments | Application | APP-118 | Market D supplier register
L-018 | DSP-22 | Decisions | Domain | DOM-06 | Logistics
L-019 | DSP-22 | Decisions | Application | APP-119 | Market D warehouse system
L-020 | ADR-088 | Decisions | Domain | DOM-10 | Corporate platforms
L-021 | ADR-088 | Decisions | Interface | INT-060 | Customer events, first producer
L-022 | ADR-018 | Decisions | Object | OBJ-07 | Price
L-023 | ADR-041 | Decisions | Object | OBJ-07 | Price
Without these rows a record is findable only by somebody who already knows it exists - which is exactly the person who does not need it.

## Derived views
Is the practice actually working
Nothing here is typed. Read it monthly; the repetition counter is the one that pays.
Decisions recorded |  |  | The base number
Decisions missing the Rejected field |  | should be 0 | The most common failure. Without it the argument returns
Decisions missing the Cost field |  | should be 0 | A decision with no stated cost was a preference
Decisions with no links |  | should be 0 | These will never surface in an impact list
Superseded decisions with no forward pointer |  | should be 0 | The trail breaks here
Open exceptions |  |  | The register's temperature
Open exceptions past expiry |  | should be 0 | The quarterly review did not happen
Open exceptions due within the warning window |  |  | This quarter's agenda, computed
Exceptions renewed with no new reason |  | should be 0 | An extension without a new reason is a rejection with better manners
Classifications recorded |  |  | The register almost nobody keeps
Assessments past their cycle |  |  | Stale judgements still being quoted as current
Disputed assessments |  |  | Not a problem. It means the anchors are doing their job
Repetition: the same topic arriving again and again
Type a topic in the yellow cells. At or above the threshold on Settings, you are not looking at an annoyance - you are looking at a missing principle.
Topic (as written in Decisions) | Times decided | Missing principle? | What it is probably telling you
Price mastership |  |  | Three decisions in three years on one object. This is a missing principle about system of record, announcing itself
Core integration |  |  | A principle about released contracts, which you may already have
Customer copies |  |  | A principle about one system of record per object
Every time-boxed record generates its own review agenda. The quarterly session does not need a facilitator deciding what to discuss - the register decides, by date.