## Read me
The architecture board registers
Two working sheets: the decision log and the exception register. Companion to the field-kit deck and the templates document - article at mehdibamou.com/publications/architecture-board-forum-system.
How to use
The secretary owns both sheets. Rows in italic gray are fictional examples showing the expected format - delete them and start at the first empty row. Yellow cells are the ones you type in; everything else is formatted or computed.
The 'Days to expiry' column recalculates from today's date. Negative numbers mean an expired exception that was not reviewed - that is a process failure, and it belongs on the next agenda.
Reading the exception register as a KPI
A register that only ever grows means the board stopped saying no - or a standard deserves to die. Extensions outnumbering closures means expiries are theater. Review expiries as the first standing item of each quarter.
Free to use and adapt - mehdibamou.com

## Decision log
No | Date | Title (state the decision) | Outcome | Conditions (what - owner - due) | Repository changes done | Linked records | Status
AB-041 | 2026-04-14 | The group consolidates on one integration platform | Approved with conditions | Sequence published - commerce architect - 30 Apr; standstill risk - O2C owner - 15 May | Yes - lifecycle + successors set | AB-042 | Open
AB-042 | 2026-04-14 | Exception: two mainframe-era order flows stay on legacy broker | Approved (exception) | Exit via order mgmt program - store systems lead - Q4 review | Yes - exception tags set | AB-041 | Open
AB-043 | 2026-04-28 | Finance target diagram re-issued with market carve-out | Approved | Diagram v1.1 attached - corporate architect - same day | Yes - v1.0 archived | - | Closed
^ start here - yellow row shows where new entries begin. Number sequentially, never reuse a number.

## Exception register
ID | Deviates from (record no) | Scope (apps / markets) | Business reason (short) | Approved | Expiry | Days to expiry | Yearly cost (EUR) | Status / outcome
AB-042 | AB-041 single integration platform | 2 order flows, markets N + S | Rewrite lands with order mgmt program; migrating twice doubles risk | 2026-04-14 | 2027-10-14 | 446 | 70000 | Active
AB-037 | AB-019 standard identity provider | Warehouse scanners, 1 site | Device fleet replacement scheduled | 2025-11-02 | 2026-06-30 | -25 | 15000 | Closing on schedule
AB-029 | AB-011 approved database list | Analytics sandbox | Trial concluded - was not renewed | 2025-06-10 | 2026-03-31 | -116 | 22000 | Expired - escalated
-46228
^ start here. At expiry the outcome is binary: closed, or extended with a new reason and a new date on the record.
Formulas:
Days to expiry = [Expiry]-TODAY()